M.Tech Thesis — Progress Report

Missing Modality + Mechanistic Interpretability on StressID

Prateek Choudhary   |   Guide: Dr. Naveen Saini

Updated — aaj ka poora kaam included

# 0. Aaj Ek Line Mein

Purana benchmark task-identity se confounded nikla. Aur jab sahi tareeke se test kiya — within-task — toh SAB kuch chance level (0.50) pe aa gaya. Purana baseline bhi, naya model bhi. Yaani aaj tak kisi ne bhi StressID pe asli within-task stress detection dikhayi hi nahi hai.

## Aaj kya-kya hua

| Kya | Kisne kiya | Nateeja |
| --- | --- | --- |
| Data audit — availability matrix | Chat (scripts) | 13 findings, 12th task mila |
| Leakage experiment | Chat (scripts) | +0.064 F1 inflation, 24/24 |
| Metadata control baselines | Chat (scripts) | Task-identity = 132 features |
| 5-modality dataset builder | Claude Code | Naya CSV + mask file |
| Physio-anchored model | Claude Code | 0.689 BAcc (pooled) |
| Overfitting fix | Claude Code | 0.635 se 0.689 |
| Anchor sweep (5 anchors) | Claude Code | RESP best, video worst |
| 10-seed stability check | Claude Code | 2 findings retract, 1 confirm |
| Within-task evaluation | Claude Code | SAB 0.50 pe — chance level |

Aaj do baar apni hi cheezein wapas leni padi — pehle do interpretability findings (10 seeds pe replicate nahi hue), phir poora performance claim (within-task pe collapse ho gaya). Ye asli science hai. Agar ye galat cheezein thesis mein chali jaatin aur panel poochta, tab problem hoti.

# 1. Data Audit — Dataset Ka Sach

Script: 01_audit_dataset.py  |  Output: outputs/audit_log.txt

## 1.1 Har file mein kitna data hai

| File | Rows | Subjects | Labeled |
| --- | --- | --- | --- |
| ecg_features.csv | 774 | 65 | 700 |
| eda_features.csv | 773 | 65 | 699 |
| resp_features.csv | 774 | 65 | 700 |
| video11tasks (mean_std) | 603 | 55 | 600 |
| HCfeatures.csv (audio) | 378 | 54 | 378 |
| all_physiological_features.csv | 773 | 65 | 699 |
| labels.csv | 700 | 64 | — |

## 1.2 Ek 12th task mila jo kisi ne count nahi kiya

Paper 11 tasks bolta hai. Data mein 12 hain. Ek 'Baseline' recording hai jo:

- 64 subjects mein physiology ke saath maujood hai

- Video aur audio bilkul nahi (0%)

- labels.csv mein bilkul nahi hai

Isse 773 vs 711 ka hisaab lag gaya:

ECG total rows        = 774
minus Baseline (64)   = 710      <- paper ka 711 (1 ka farak)
minus unlabeled       = 700      <- labels mein itne hi hain

Par paper ka 715 impossible hai. Sirf 700 tasks ke labels hain. 715 tasks pe supervised model train ho hi nahi sakta.

## 1.3 Modality availability

| Modality | Present | % of 777 rows | % of 700 labeled |
| --- | --- | --- | --- |
| ECG | 774 | 99.6% | 100% |
| EDA | 773 | 99.5% | 99.9% |
| RESP | 774 | 99.6% | 100% |
| Video | 603 | 77.6% | 85.7% |
| Audio | 378 | 48.6% | 54.0% |

Note: Claude Code ne 85.7% aur 54% report kiya, maine 77.6% aur 48.6%. Dono sahi hain — Claude ne 700 labeled tasks pe count kiya, maine 777 total rows pe. Koi contradiction nahi.

## 1.4 Missingness structured hai — random nahi

Sirf 6 availability patterns hain, 31 possible mein se:

11111  n=370   sab kuch maujood
11110  n=229   audio nahi
11100  n=167   audio + video nahi
11101  n=  7   video nahi
00010  n=  3   sirf video
10111  n=  1   EDA nahi

Aur missingness ka do-layer structure hai:

- Task-level — audio sirf 7 talking tasks mein (protocol)

- Subject-level — 10 subjects ke paas video kabhi nahi, 11 ke paas audio kabhi nahi

Poori literature random masking use karti hai. Yahan missingness subject ke saath jaati hai. Ye tumhara sabse strong benchmark argument hai.

## 1.5 Validation — 370 exact match

Saari 5 modalities present = 370 tasks. Paper bhi 370 bolta hai. Ye proof hai ki pipeline sahi chal rahi hai.

# 2. Leakage Experiment — Sabse Bada Result

Script: 02_leakage_experiment.py  |  Output: outputs/leakage_log.txt

## 2.1 Leaky numbers paper ko exactly reproduce karte hain

| Modality | Paper (Table 2) | Leaky split | Clean split |
| --- | --- | --- | --- |
| Physio HC + RF | 0.73 / 0.72 | 0.725 / 0.726 | 0.680 / 0.694 |
| Video AUs + kNN | 0.70 / 0.69 | 0.687 / 0.685 | 0.539 / 0.548 |
| Audio HC + kNN | 0.67 / 0.60 | 0.695 / 0.610 | 0.574 / 0.503 |

Teeno modalities pe leaky split paper ke numbers +/-0.02 ke andar reproduce karta hai. Clean split nahi karta. Ye ab dava nahi, PROOF hai ki published baselines subject leakage se aaye hain.

Random splits mein average 59.3 out of 64 subjects dono taraf the — yaani 93% subjects test mein bhi the aur train mein bhi.

## 2.2 Har combination mein drop — 24 out of 24

Average inflation: F1 +0.064, Balanced Accuracy +0.048. Ek bhi exception nahi.

## 2.3 Clean split pe ranking hi ulat gayi

| Rank | Leaky | Clean |
| --- | --- | --- |
| 1 | ECG (0.735) | RESP (0.686) |
| 2 | physio_all (0.725) | physio_all (0.680) |
| 3 | RESP (0.713) | ECG (0.664) |
| 4 | Audio (0.695) | Audio (0.635) |
| 5 | Video (0.687) | EDA (0.632) |
| 6 | EDA (0.680) | Video (0.600) |

Aur clean split mein RESP akela (0.686) poore physio_all (0.680) ko beat karta hai — 62 features 132 se better. Leakage ne ye chhupa liya tha.

Iska matlab: agar koi researcher is benchmark pe modality selection karega, wo GALAT modality chunega.

## 2.4 Audio chance level pe hai

Clean split pe audio ka balanced accuracy: RF 0.495, SVC 0.489, KNN 0.503.

0.50 = sikka uchhalna. Audio mein subject-independent stress signal hai hi nahi. F1 (0.53-0.64) theek lagta hai sirf class imbalance (263/115) ki wajah se.

## 2.5 KNN sabse zyada girta hai — aur reason hai

| Modality | KNN drop |
| --- | --- |
| Video | 0.148 |
| Audio | 0.122 |
| ECG | 0.086 |
| RESP | 0.020 |

KNN nearest neighbour dhoondhta hai — aur wo aksar usi bande ka doosra task hota hai. Video/audio sabse zyada girte hain kyunki chehra aur awaaz sabse zyada identifying hote hain. RESP sabse kam — saans ka pattern kam personal hai.

# 3. Control Baselines — Aur Bada Result

Script: 03_presence_baseline.py  |  Output: outputs/presence_log.txt

Sawaal: reported performance ka kitna hissa asli signal se hai, aur kitna sirf metadata se?

| Baseline | Input | F1 | BAcc |
| --- | --- | --- | --- |
| 1. majority | kuch nahi | 0.332 | 0.500 |
| 2. presence | 5 bits (kaunsi modality hai) | 0.652 | 0.656 |
| 3. task identity | 11 bits (kaunsa task hai) | 0.685 | 0.695 |
| 4. presence + task | 16 bits | 0.682 | 0.689 |
| 5. asli physio | 132 features | 0.680 | 0.694 |

Task ka naam jaanna — 11 bits, koi signal nahi — 132 physiological features jitna hi accurate hai. Difference: 0.001.

## 3.1 Iska matlab kya hai — aur kya NAHI hai

Ye ye NAHI kehta ki physiology bekaar hai. ECG stress pe react karta hai, ye science hai.

Ye ye kehta hai: is evaluation protocol mein — jahan saare 11 tasks pool karke ek task-level self-report label predict karna hai — label bahut had tak task se hi decide ho jaata hai. Benchmark ye distinguish hi nahi kar sakta ki model ne ECG padha, ya bas ye pehchana ki 'ye Counting2 hai'.

Aur deployment mein task ka naam pata nahi hota. Toh jo benchmark task-identity se solve ho jaaye, wo deployable capability measure nahi kar raha.

## 3.2 Honest note

Presence (0.656) task-identity (0.695) ka hi coarse version hai — 5 patterns vs 11 tasks. Aur presence+task (0.689) task akele se better nahi hai. Matlab presence koi naya signal nahi deta. Isko alag finding mat batana.

## 3.3 Cross-check pass

Script 02 ne physio_all RF clean pe 0.680 / 0.694 diya. Script 03 ne bhi 0.680 / 0.694. Do alag code paths, identical result.

# 4. Claude Code Ka Kaam — Naya Model

## 4.1 Jo files bani

| File | Kya karti hai |
| --- | --- |
| Dataset/ | labels + demographics ki local copy |
| Feature Extraction/build_multimodal_dataset.py | 5 modalities ko jodta hai, missing ko drop nahi karta — NaN + mask rakhta hai |
| Classification/dataset_audit.py | Claude Code ka apna audit |
| Method/adapt_variant/data.py | Data loading + subject-wise split |
| Method/adapt_variant/model.py | Physio-anchored ADAPT variant |
| Method/adapt_variant/train.py | Two-stage training (anchoring + fusion) |
| Method/adapt_variant/interpretability.py | Shapley + head ablation |
| Method/adapt_variant/anchor_sweep.py | 5 anchors ka controlled comparison + significance test |
| Method/adapt_variant/interpretability_stability.py | 10-seed stability check |
| Classification/task_identity_baseline.py | Task-identity confound ka independent verification |
| Classification/metrics_utils.py | Within-task balanced accuracy metric — shared |

Original notebooks touch nahi kiye gaye — sab naye files mein hai.

## 4.2 Overfitting fix

Problem: train 90%+, test sirf 63.5%. Model raat ko sab ratt raha tha.

Kya kiya:

- Inner validation split (subject-wise) — early stopping ke liye

- Early stopping with patience, best weights restore

- Dropout 0.3 encoder mein

- Encoder hidden dim 128 se 64

|  | Train | Val | Test |
| --- | --- | --- | --- |
| Pehle | ~0.90 | — | 0.635 |
| Ab | 0.737 | 0.728 | 0.689 |

Test accuracy sirf gap kam nahi hua — actually BADH gaya (0.635 se 0.689). Matlab asli generalization improve hui, sirf regularization se number chhupa nahi.

## 4.3 Anchor sweep — 5 anchors, same folds

Sabhi 5 modalities ko anchor banake test kiya, bilkul same folds pe. 25 seconds mein poora.

| Anchor | Test BAcc | Rank |
| --- | --- | --- |
| RESP | 0.696 (+/- 0.008) | 1 — sabse stable bhi |
| EDA | 0.691 (+/- 0.018) | 2 |
| ECG | 0.689 (+/- 0.018) | 3 |
| Audio | 0.678 (+/- 0.016) | 4 |
| Video | 0.670 (+/- 0.019) | 5 — sabse zyada overfit |

Teeno physiology anchors (RESP, EDA, ECG) dono behavioural anchors (video, audio) se better hain — 4 out of 5 folds mein. Video ka train 0.761 sabse zyada hai par test sabse kam — matlab wo sabse zyada ratt raha hai.

Ye ADAPT paper ke 'video anchor best hai' claim ke against hai — kam se kam StressID ke is setup mein.

### Honest caveat — significance

Paired t-test across 5 folds:

- RESP vs Video: p = 0.062 (4/5 folds mein jeeta)

- RESP vs Audio: p = 0.057 (4/5 folds mein jeeta)

- ECG/EDA comparisons: p = 0.13 se 0.34

p = 0.062 conventional 0.05 threshold se upar hai. Direction consistent hai par statistically significant NAHI hai. Sirf 5 folds hain, 13 test subjects per fold — power kam hai. Ye honestly likhna, warna reviewer pakad lega.

Physio-anchor ka practical case (availability, privacy, wearable) statistics se independent hai — wo argument akela bhi khada hai.

## 4.4 Interpretability — pehle galat, phir sahi

### Pehla attempt (overfit model se) — YE GALAT THA

Pehle jo results aaye the:

- EDA ka contribution Math aur Counting mein sabse zyada (+0.108)

- 4 heads mein se head 2 important hai

Ye dono overfit model se the. Overfitting fix karne ke baad dobara chalaya — dono REPLICATE NAHI HUE. Isliye dono claims retract kar diye gaye.

### Multi-seed stability check — asli tareeka

10 alag training seeds pe chalaya. Test subjects har baar wahi 10 (split seed 1999 fixed). Sirf training randomness badli — weight init, validation split, dropout. Poora run 13 second.

Logic: agar koi finding sach hai toh 10 alag models mein dikhna chahiye. Agar sirf ek run mein dikhe, wo lottery hai.

### Jo STABLE nikla — ab bharose se likh sakte ho

| Modality | Mean utilization | Std | Top kitni baar (10 mein se) |
| --- | --- | --- | --- |
| RESP | +0.0486 | 0.0185 | 5 |
| ECG | +0.0419 | 0.0140 | 5 |
| Video | +0.0291 | 0.0095 | 0 |
| EDA | -0.0070 | 0.0091 | 0 |
| Audio | +0.0008 | 0.0108 | 0 |

Note: pehle is table mein std thoda alag likha tha (0.0195, 0.0148...). Wo sample std (ddof=1) tha, ye population std (ddof=0) hai — ratio bilkul sqrt(10/9) ka hai. Dono sahi hain. Thesis mein ek hi convention use karna, aur likhna kaunsa use kiya.

Aur ek correction: sabse stable modality EDA hai (std 0.0091), video nahi (0.0095). Farak bahut chhota hai par likhne se pehle sahi karna. Video sirf un modalities mein sabse stable hai jinka mean clearly positive hai.

Do bilkul alag analyses ne same jawab diya: anchor sweep (accuracy se) aur Shapley utilization (contribution se) — dono RESP aur ECG ko upar rakhte hain. Ye convergence hai, aur yahi isko trustworthy banata hai.

Do aur solid baatein:

- EDA ka contribution NEGATIVE hai (-0.0070) — matlab EDA hataane se model behtar ho jaata hai. Sirf kam useful nahi, actively nuksan kar raha hai.

- Audio ~0.0008 = practically zero. Ye leakage experiment se match karta hai jahan audio clean split pe chance level (0.49 BAcc) pe tha. Do taraf se same conclusion.

### Jo REPLICATE NAHI hua — retract

EDA-Math wala claim, 10 seeds mein:

- Math: EDA positive 0 out of 10 seeds (hamesha negative ya zero)

- Counting1: 4/10, Counting2: 3/10, Counting3: 7/10 — koi consistent pattern nahi, bas noise

Head-importance bhi stable nahi:

- head 2 sabse zyada baar chuna gaya — par sirf 4/10 baar

- head 3: 3 baar, head 0: 2 baar, head 1: 1 baar

Koi ek head consistently important nahi hai. Par ye khud ek valid finding hai: is scale pe individual attention heads reliably specialize nahi karte. Thesis mein likh sakte ho ki head-level claims yahan justify nahi hote jab tak model scale na badhe.

### Aur ek honest number

Test accuracy khud seed-to-seed hilti hai: 0.679 +/- 0.017 (min 0.644, max 0.712).

Matlab ek single run ka number +/- 0.02-0.03 easily shift ho sakta hai. Kabhi bhi single-seed number ko final claim ki tarah mat present karna — hamesha multi-seed average.

## 4.5 Do tension jinka jawab thesis mein dena padega

### Tension 1 — EDA anchor mein #2, contribution mein last

EDA anchor banane pe 0.691 (dusra best). Par uska apna contribution -0.0070 (sabse kharaab).

Possible explanation: anchor ka kaam alignment target banna hai, apna signal contribute karna nahi. Ek modality achha reference frame de sakti hai bina khud informative hue. Par ye likhna padega, warna reviewer poochega.

### Tension 2 — Video contribution mein #3, anchor mein last

Video ka utilization +0.0291 hai (aur sabse stable, std sirf 0.0100). Par anchor banane pe sabse kharaab (0.670).

Yaani video useful hai jab wo INPUT ho, par kharaab hai jab wo ANCHOR ho.

Ye dono milake ek asli insight hai: 'achha anchor' aur 'achhi modality' alag cheezein hain. ADAPT paper ne ye distinction kabhi nahi banayi. Agar tum isko clean tareeke se dikha do, ye apne aap mein ek contribution hai.

# 5. Within-Task Evaluation — Sab Kuch Badal Gaya

Ye poori thesis ka sabse important section hai. Isko dhyan se padhna.

## 5.1 Sawaal kya tha

Pooled evaluation mein saare 11 tasks ek saath mix karke test hota hai. Par tasks ka apna stress rate alag-alag hai:

- Counting2, Stroop — 76.6% stress

- Relax — 12.9% stress, Breathing — 17.2%

Toh model sirf ye pehchan ke ki 'ye Counting2 hai' achha score la sakta hai — bina kisi physiological signal ke.

Within-task evaluation: har task ke ANDAR alag se balanced accuracy nikalo, phir average karo. Ab task-identity ka shortcut kaam nahi karega, kyunki task constant hai.

## 5.2 Metric sahi hai — sanity check pass

Task-identity-only baseline ko within-task metric pe chalaya. Result: exactly 0.500 +/- 0.000.

Ye mathematically expected hai — ek task ke andar agar hamesha ek hi class predict karo, toh ek class ka recall 1 aur doosre ka 0, average 0.50. Matlab metric ka construction bilkul sahi hai.

## 5.3 Asli result

| Model | Pooled BAcc | Within-task BAcc |
| --- | --- | --- |
| Task-identity only (majority vote) | 0.705 | 0.500 +/- 0.000 |
| Task-identity only (RF one-hot) | 0.689 | 0.500 +/- 0.000 |
| Physio RF baseline (132 features) | 0.706 +/- 0.057 | 0.504 +/- 0.019 |
| Deep model — ECG anchor | 0.689 +/- 0.018 | 0.504 +/- 0.008 |
| Deep model — RESP anchor | 0.696 +/- 0.016 | 0.501 +/- 0.010 |

Teeno asli models — purana baseline aur dono anchors — within-task pe exactly chance (0.50) pe hain. Task-identity-only baseline se koi bhi statistically alag nahi hai.

## 5.4 Kya kisi ek task mein signal chhupa hai?

Har task alag se check kiya (11 tasks x 2 anchors = 22 comparisons):

- ECG anchor: 0.476 (Reading/Relax) se 0.547 (Counting2)

- RESP anchor: 0.465 (Math) se 0.525 (Counting3)

Best case Counting2 + ECG = 0.547 +/- 0.057. Par ye 22 comparisons mein se best hai. Multiple-comparison correction ke baad ye noise hai.

Kai tasks 0.5 se NEECHE hain — bilkul waisa jaisa pure noise mein hota hai.

## 5.5 Ye result underpowered toh nahi hai?

Ye sawaal poochna zaroori hai — kya signal nahi hai, ya detect karne ki taakat nahi hai?

| Model | Mean | Std (5 folds) | 95% CI |
| --- | --- | --- | --- |
| Physio RF | 0.504 | 0.019 | [0.487, 0.521] |
| Deep ECG | 0.504 | 0.008 | [0.497, 0.511] |
| Deep RESP | 0.501 | 0.010 | [0.495, 0.513] |

CI ka upper end ~0.52 hai. Matlab agar asli effect 0.55 ka bhi hota, toh pakda jaata. Ye result well-powered hai — 'signal nahi mila' ka matlab sach mein 'signal nahi hai' (at least in features).

Ek cheez abhi check karni hai: kuch task-folds mein shayad ek hi class ho (jaise Relax mein 13 mein se sirf 1 stressed). Aise cases mein BAcc undefined ya degenerate ho jaata hai. Code kaise handle karta hai, ye confirm karna chahiye.

## 5.6 Isse interpretability findings bhi reinterpret karne padenge

Pehle bola tha: 'ECG aur RESP sabse useful modalities hain' (Shapley se, 10 seeds pe stable).

Par wo Shapley POOLED predictions ko explain kar raha tha. Aur ab pata hai ki pooled predictions ~93% task-identity se explained hain.

Toh 'ECG/RESP sabse useful' ka matlab shayad ye hai ki wo model ko TASK pehchanne mein help karte hain — na ki genuine stress signal dete hain. Numbers galat nahi hain, par interpretation ab uncertain hai. Thesis mein ye caveat likhna zaroori hai.

## 5.7 Ek verification note

Claude Code ne poocha tha ki 'audio clean split pe 0.49 BAcc' wala number kahan se aaya. Wo verified hai — script 02_leakage_experiment.py ke output se, groupshuffle mode mein:

audio [groupshuffle]
  KNeighborsClassifier   BAcc 0.503 (+/-0.041)
  MLPClassifier          BAcc 0.585 (+/-0.070)
  RandomForestClassifier BAcc 0.495 (+/-0.029)
  SVC                    BAcc 0.489 (+/-0.029)

Source file: outputs/leakage_log.txt aur outputs/leakage_raw_results.csv.

# 6. Ab Aage Kya — Thesis Ki Direction

Ye ab technical decision nahi, thesis ki direction ka decision hai. Guide se discuss karke lena.

## 6.1 Pehle ye samjho — ye FAILURE nahi hai

Pehli nazar mein lagta hai ki sab bekaar gaya. Par ulta socho:

- Tumne dikhaya ki StressID ke published baselines leakage se inflated hain

- Tumne dikhaya ki jo bacha wo task-identity confound hai

- Tumne dikhaya ki sahi protocol pe purana baseline BHI chance pe hai

- Tumne ek naya evaluation protocol banaya jo confound ko neutralize karta hai

Ek negative result jo rigorously prove kiya gaya ho, wo ek positive result se zyada valuable hota hai jo galat protocol pe mila ho. Aur ye poore field pe lagu hota hai, sirf tumhare model pe nahi.

## 6.2 Teen possible thesis narratives

### Option A — Benchmark critique paper (sabse safe)

Thesis ka core: 'StressID benchmark task-identity se confounded hai, aur koi bhi method — published ya naya — within-task stress detection nahi karta.'

- Contribution 1: leakage audit + corrected splits

- Contribution 2: within-task evaluation protocol

- Contribution 3: sab methods ka honest re-evaluation

Risk: kam. Ye kaam ho chuka hai. Bas likhna hai.

### Option B — Protocol + architecture (balanced)

Option A + missing-modality architecture ko engineering contribution ki tarah present karo, performance claim ke bina.

Architecture valid hai — masked transformer, physio anchoring, 5-modality support. Wo alag se defend ho sakti hai.

Risk: medium. Panel poochega 'accuracy kyun nahi badhi' — par tumhare paas jawab hai.

### Option C — Signal dhoondhne ki koshish (sabse risky)

Aur mehnat karo taaki within-task signal mile:

- affect3-class target try karo — shayad wahan confound kam ho

- Raw signals se seekho, handcrafted features se nahi (features already averaged hain, fine detail kho gayi hai)

- Within-subject normalization — har bande ke apne baseline se difference lo

Risk: zyada. Ho sakta hai signal mile hi na — 64 subjects, per-task per-fold sirf 12-13 log.

## 6.3 Mera suggestion

Option B pe jao, aur Option C mein se sirf DO cheezein try karo (2 hafte cap):

- 1. Within-subject normalization — har feature se us bande ka Baseline task ghata do. Ye sabse promising hai kyunki physiological signals mein individual variation bahut zyada hoti hai, aur wahi signal ko dhak deti hai.

- 2. affect3-class target — 15 minute ka kaam hai, poori pipeline already ready hai.

Agar in dono se bhi kuch nahi mila, toh Option A/B pe likhna shuru kar do. Aur wo bhi ek strong thesis hai.

## 6.4 Chhote technical kaam

- Degenerate task-folds check karo — kya kisi task-fold mein ek hi class hai?

- Within-task AUC bhi nikalo — BAcc se zyada power hoti hai

- anchor_sweep.py ko within-task metric ke saath dobara chalao

- Shapley ko within-task predictions pe recompute karo

# 7. Professor Ko Kya Dikhana Hai

## Slide 1 — Benchmark toota hua hai

- Leaky split paper ko +/-0.02 mein reproduce karta hai, clean nahi

- 24 out of 24 combinations mein drop

- Sahi function (make_nclassif, GroupKFold) code mein hai par kabhi call nahi hota

## Slide 2 — Aur jo bacha wo bhi shortcut hai

- Task-identity (11 bits) = 132 physiological features

- Audio presence 37-point signal deta hai

- Clean split pe audio chance level (0.49) pe hai

## Slide 3 — Sahi protocol pe SAB chance level pe hain

- Within-task evaluation: physio RF 0.504, deep model 0.504, RESP anchor 0.501

- Task-identity baseline within-task = 0.500 (by construction, sanity check pass)

- Koi bhi task individually signal nahi deta (22 comparisons check kiye)

- Result well-powered hai — 95% CI upper ~0.52, toh 0.55 ka effect bhi pakda jaata

## Slide 4 — Kya bacha, kya aage

- Missing-modality architecture valid hai as engineering contribution

- Within-task protocol khud ek contribution hai

- Do interpretability findings retract kiye (10 seeds pe replicate nahi hue)

- Aage: within-subject normalization + affect3-class try karna

## Ye line zaroor bolna

"Sir, maine benchmark ka poora audit kiya. Teen cheezein mili — subject leakage, task-identity confound, aur variance reporting ki galti. Phir maine within-task evaluation protocol banaya jo confound ko neutralize karta hai. Us protocol pe StressID ka apna baseline BHI chance level pe hai, mera naya model bhi. Ye disappointing hai par maine ise chhupaya nahi — kyunki agar poore field ka evaluation hi confounded hai toh wo apne aap mein reportable finding hai. Do interpretability findings maine khud retract kiye kyunki 10 seeds pe replicate nahi hue."

Sirf keede nikalne wala student aur audit karne wala student — panel ko farak dikhta hai. Aur apni hi galti khud pakadne wala student sabse strong dikhta hai.

# 8. Saare Findings — Ek Jagah

| # | Finding | Type |
| --- | --- | --- |
| 1 | Subject leakage — sahi function hai par call nahi hota | Bug |
| 2 | Dead shuffle + deterministic GroupKFold = fake variance | Bug |
| 3 | Saved Results stale (8 splits, default classifiers) | Repro |
| 4 | Audio-presence shortcut: 69.6% vs 32.6% stress | Novel |
| 5 | 64 subjects labeled, paper 65 bolta hai | Data |
| 6 | Sirf 700 labels — paper ka 715 impossible | Data |
| 7 | EDA mein 1 recording kam — chhupa hua missing case | Data |
| 8 | SMOTE protocol notebooks ke beech inconsistent | Method |
| 9 | Saved numbers paper se reproduce nahi hote | Repro |
| 10 | 12th task (Baseline) — undocumented aur unlabeled | Data |
| 11 | Leaky split paper ko exactly reproduce karta hai | Novel |
| 12 | Missingness subject-level hai, task-level nahi | Novel |
| 13 | Sirf 6 availability patterns, 31 possible mein se | Data |
| 14 | Clean split pe modality ranking ulat jaati hai | Novel |
| 15 | Audio clean split pe chance level (0.49 BAcc) | Novel |
| 16 | Task-identity (11 bits) = 132 physio features | Novel |
| 17 | Physiology anchors > video/audio anchors (p=0.063) | Method |
| 18 | ECG + RESP sabse informative — 2 alag analyses se confirm | Novel |
| 19 | EDA ka contribution negative (-0.007), 10 seeds pe stable | Novel |
| 20 | Audio contribution ~0 — leakage experiment se match | Novel |
| 21 | Attention heads reliably specialize nahi karte is scale pe | Novel |
| 22 | Achha anchor aur achhi modality alag cheezein hain | Novel |
| 23 | Within-task pe physio RF 0.504 — chance level | Novel |
| 24 | Within-task pe deep model 0.504 — chance level | Novel |
| 25 | Koi bhi single task signal nahi deta (22 comparisons) | Novel |
| 26 | Result well-powered — CI upper ~0.52, 0.55 pakda jaata | Method |
| R1 | RETRACTED: EDA-Math contribution (overfit artifact) | Retract |
| R2 | RETRACTED: head 2 important (seed lottery) | Retract |
| R3 | UNCERTAIN: ECG/RESP 'most useful' — shayad task-identity | Caveat |

# 9. Saari Files Aur Paths

## Chat ki taraf se (Classification/ folder mein)

Classification/
  01_audit_dataset.py           -> outputs/audit_log.txt
  02_leakage_experiment.py      -> outputs/leakage_log.txt
  03_presence_baseline.py       -> outputs/presence_log.txt
  make_classification_fixed.py  (3 split modes + leak audit)
  outputs/
    availability_matrix.csv
    missingness_per_task.csv
    availability_patterns.csv
    file_summary.csv
    leakage_raw_results.csv
    leakage_summary.csv
    presence_baseline_summary.csv

## Claude Code ki taraf se

Dataset/                              (labels ki local copy)
Feature Extraction/
  build_multimodal_dataset.py
  Features/multimodal_5modality_features.csv
  Features/multimodal_5modality_mask.csv
Classification/dataset_audit.py
Method/adapt_variant/
  data.py  model.py  train.py
  interpretability.py  anchor_sweep.py
  interpretability_stability.py
  outputs/
    results_binary-stress_anchor-ecg.json
    anchor_sweep_binary-stress.json
    interpretability_stability_binary-stress_anchor-ecg.json
    shapley_utilization_binary-stress.csv
    shapley_by_task_binary-stress.csv
    head_ablation_binary-stress.csv

Thesis mein numbers hamesha in JSON files se lena, memory se nahi. Sab reproducible hain, koi hardcoded value nahi.

## Chalane ke commands

cd Classification
mkdir -p outputs
python3 -u 01_audit_dataset.py 2>&1 | tee outputs/audit_log.txt
python3 -u 02_leakage_experiment.py 2>&1 | tee outputs/leakage_log.txt
python3 -u 03_presence_baseline.py 2>&1 | tee outputs/presence_log.txt

Note: -u flag zaroori hai, warna pipe ke saath output buffer ho jaata hai aur screen pe kuch nahi dikhta.

# 10. Teen Papers Se Kya Samjha

## StressID (NeurIPS 2023) — tumhara dataset

- 65 subjects, 11 tasks (actually 12), 3 modality types

- Baselines: physio 0.73, video 0.70, audio 0.67 F1

- Ab pata hai ye numbers leaky split se aaye hain

## MLMM Survey (TMLR 2026) — 354 papers ka review

- Missing modality ke do rasta: generate karo, ya available se kaam chalao

- Section 7.2: koi nahi jaanta ki recovered modality actually use hoti hai ya nahi

- 354 papers mein ek bhi mechanistic interpretability use nahi karta — ye genuine gap hai

- Sirf 36.4% papers incomplete data pe train karte hain

## ADAPT (MIDL 2024) — main baseline

- Ek anchor modality choose karo, baaki ko usse align karo

- Masked transformer — missing modality ko attention mein ignore kar do

- Unhone video anchor use kiya, physiology kabhi try nahi ki

- Paper khud kehta hai 'any modality can be the anchor' — tum usko test kar rahe ho

Kaafi kaam ho gaya hai. Ab within-task evaluation — wo aakhri missing piece hai.